## Efficiency_Plan
Dept | Program Name | PM Responsible | Program Code | Baseline | Baseline Start | Baseline End | Estimated Hrs (Hours) | Actual Hrs (Hours) | Effort Variance (Hours) | Productivity Index (Hours) | Total Effort Saved from opportunities (Hours) | Total Effort Saved from opportunities (Euros) | Total Cost Saved from opportunities (Euros) | Reuse of Reference Library / Solutions (Hours) | Technical Competency Improvement (Hours) | AI Assisted / Copilot Usage (Hours) | Automation of Testing (Unit / Component / System) (Hours) | Automation of Reviews (Hours) | Automation of Build & Release Process (CI/CD / DevX) (Hours) | Automation - Others (if any) (Hours) | Usage of Simulators / Tools / Infrastructure (Hours) | Software Development Life Cycle (SDLC) Process Improvement / Lean Process (Hours) | Opportunities Realized in Reducing Inefficiency (Hours)
DTech | MOON | Nitin Naghate | PGA001 | 1.5 | 2021-07-05 | 2024-12-09 | 113404 | 117571 | -4167 | 1.0367 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DTech | MOON | MUTTALLI Rakesh v | PGA001 | 1.5.1 | 2024-08-01 | 2025-05-27 | 18244 | 18170 | 74 | 0.99594 | 74 | 1850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74 | 0 | 0 | 0
TET | RIGHT | Nandan Nair | PGA005 | 4.2.0 | 2024-04-01 | 2024-06-30 | 20160 | 18867 | 1293 | 0.93586 | 2073 | 51825 | 0 | 123 | 20 |  | 1920 | 10
TET | RIGHT | Nandan Nair | PGA005 | 4.3.0 | 2024-07-01 | 2024-09-30 | 21600 | 21389 | 211 | 0.99023 | 2843 | 71075 | 0 | 123 | 40 | 750 | 1920 | 10
TET | RIGHT | Nandan Nair | PGA005 | 4.4.0 | 2024-10-01 | 2024-12-31 | 17760 | 16720 | 1040 | 0.94144 | 7063 | 176575 | 0 | 123 | 60 | 750 | 1920 | 10 | 3200 |  |  | 1000
TET | RIGHT | Nandan Nair | PGA005 | 4.5.0 | 2025-01-01 | 2025-03-31 | 17280 | 16444 | 836 | 0.95162 | 7563 | 189075 | 0 | 123 | 80 | 750 | 2400 | 10 | 3200 |  |  | 1000
SSsys | DMS | JAHAGIRDAR Vaidehi | PGA019 | 2.4 | 2024-02-01 | 2025-07-25 | 168960 | 153410 | 15550 | 0.90797 | 488 | 12200 | 150000 |  |  |  | 208 |  | 120 | 150 |  |  | 10
SSsys | RBC MSS | Yogish V | PGA302 | 3.3.2 | 2024-03-20 | 2024-10-25 | 1080 | 1080 | 0 | 1 | 0 | 0 | 0
DTech | DAS | Chandrashekar BC | PGA029 | 4.4.0 | 2024-07-22 | 2025-02-21 | 5256 | 4718 | 538 | 0.89764 | 500 | 12500 | 0 | 200 | 200 | [6 empty] | 100
SSsys | U400 MSS | Yogish V | PGA048 | Mumbai-Pune 6.5.0.3 | 2025-03-03 | 2025-04-25 | 714 | 714 | 0 | 1 | 0 | 0 | 0
DTech | Concerto | Sivakumar Jegannathan | PGA253 | Baseline 1 | 2024-04-01 | 2025-01-09 | 45824 | 41961 | 3863 | 0.9157 | 3095.55 | 77388.75 | 0 | 114.75 | 127.5 | 734.4 | 540 | 428.4 | 178.5 | 0 | 972 | 0 | 0
DTech | Concerto | Sivakumar Jegannathan | PGA253 | Baseline 2.0 | 2025-01-10 | 2025-05-09 | 37131 | 38998 | -1867 | 1.0503 | 3619.21 | 90480.25 | 0 | 242.25 | 255 | 456.96 | 240 | 272 | 153 | 272 | 1728 | 0 | 0
AI | MDP | Ekantharaja Y | PGA288 | 3.5.1 | 2024-01-10 | 2024-06-21 | 10788 | 10216 | 572 | 0.94698 | 512 | 12800 | 0 | [5 empty] | 512
AI | MDP | Ekantharaja Y | PGA288 | 4.0.0 | 2024-06-24 | 2025-02-14 | 13440 | 11520 | 1920 | 0.85714 | 1920 | 48000 | 0 | [5 empty] | 640 |  |  | 1280
Urban | Fluence | Raviprasad Y | RDZ292 | 1.7.1 | 2025-01-01 | 2025-03-21 | 5431 | 5261 | 170 | 0.9687 | 170 | 4250 | 0 |  |  |  | 170
Urban | Fluence | Raviprasad Y | PGA045 | 2.1.2.3 | 2025-01-23 | 2025-04-28 | 6659 | 5950 | 709 | 0.89353 | 500 | 12500 | 0 |  |  |  | 500
Urban | Fluence | Raviprasad Y | RDZ292 | 1.7.0 | 2024-07-12 | 2024-12-05 | 3970 | 3485 | 485 | 0.87783 | 485 | 12125 | 0 |  |  |  | 485
Urban | Fluence | Raviprasad Y | RDZ292 | 1.8.1 | 2025-02-07 | 2025-06-30 | 3043 | 3028 | 15 | 0.99507 | 100 | 2500 | 0 |  |  |  | 100
Urban | Fluence | Raviprasad Y | RD-Z291 | 2.0.2 | 2024-03-26 | 2024-07-05 | 10837 | 10388 | 449 | 0.95857 | 400 | 10000 | 0 |  |  |  | 400
Mainline | ERTMS: RBC | Prashanth KHR | PGA024 | 1.1.0 | 2024-04-05 | 2025-03-19 | 103480 | 102174 | 1306 | 0.98738 | 2100 | 52500 | 0 |  |  |  | 1500 |  | 600
Mainline | ERTMS:EVC3 | Prashanth KHR | PGA073 | 1.2.0 | 2024-06-01 | 2024-11-30 | 36720 | 34872 | 1848 | 0.94967 | 900 | 22500 | 0 |  |  |  | 600 |  | 300
Mainline | ERTMS: ONB: OCA | Prashanth KHR | PGA073 | 10.1.0 | 2023-11-20 | 2024-09-16 | 36720 | 36202 | 518 | 0.98589 | 800 | 20000 | 0 |  |  |  | 600 | 200
Mainline | ATO | Prashanth KHR | PGA073 | 1.5.0 | 2024-11-19 | 2025-05-30 | 19000 | 18347 | 653 | 0.96563 | 653 | 16325 | 0 |  |  |  | 325 | 300 |  | 28
Mainline | GE | Prashanth KHR | PGA024 | 1.0.0 | 2023-12-19 | 2024-12-13 | 17200 | 17400 | -200 | 1.0116 | 0 | 0 | 0
Mainline | CIXL-M | Shanthi Kalarikkal | PGA026 | CIXLM BL5.1 | 2024-04-01 | 2025-03-01 | 48222 | 43953 | 4269 | 0.91147 | 3900 | 97500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3900 | 0 | 0 | 0
Mainline | CIXL-M | Shanthi Kalarikkal | PGA026 | CIXLM BL5.0, CIXLM BL5.1 | 2023-04-01 | 2024-03-01 | 43494 | 41584 | 1910 | 0.95609 | 2700 | 67500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2700 | 0 | 0 | 0
Mainline | CIXL-M | Shanthi Kalarikkal | PGA026 | CIXLM BL5.0, CIXLM BL5.1 | 2022-04-01 | 2023-03-01 | 37882 | 35182.8 | 2699.2 | 0.92875 | 1350 | 33750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1350 | 0 | 0 | 0
DTech | OPERA | Saket Agrawal | PG0032 | OPERA 8.3.0 | 2023-04-01 | 2024-03-31 | 34842 | 33188 | 1654 | 0.95253 | 808 | 20200 | 0 | 200 | 120 |  | 488
DTech | OPERA | Saket Agrawal | PG0032 | OPERA 8.0.1 | 2024-06-01 | 2025-06-06 | 3718 | 3391 | 327 | 0.91205 | 190 | 4750 | 0 | 150 | 40
DTech | OPERA | Saket Agrawal | PG0032 | OPERA 8.4.0 | 2024-04-01 | 2026-04-30 | 29096 | 28483 | 613 | 0.97893 | 360 | 9000 | 0 | 180 | 80 |  |  |  | 100
Mainline | ATO | Prashanth KHR | PGA073 | 1.6.0 | 2025-06-03 | 2025-09-25 | 6800 | 7098 | -298 | 1.0438 | 0 | 0 | 0
Mainline | ERTMS:RBC ASW | Prashanth KHR | PGA024 | 1.1.0 | 2025-04-01 | 2026-01-09 | 84250 | 82200 | 2050 | 0.97567 | 1600 | 40000 | 0 |  | 500 |  |  | 350 | 350 | 400
Mainline | ERTMS:EVC3 | Prashanth KHR | PGA073 | 1.3.0 | 2024-12-10 | 2025-10-17 | 16900 | 16684.5 | 215.5 | 0.98725 | 216 | 5400 | 0 |  |  |  | 216
Mainline | ERTMS: ONB: OCA | Prashanth KHR | PGA073 | 10.2.0 | 2024-09-23 | 2025-07-30 | 25100 | 25086 | 14 | 0.99944 | 14 | 350 | 0 |  |  |  |  | 14
TET | RIGHT | Nandan Nair | PGA005 | 5.0.0 | 2025-04-01 | 2025-06-30 | 19614 | 17326 | 2288 | 0.88335 | 7573 | 189325 | 0 | 123 | 90 | 750 | 2400 | 10 | 3200 | 1000
TET | RIGHT | Nandan Nair | PGA005 | 5.1.0 | 2025-07-01 | 2025-09-30 | 18050 | 16059 | 1991 | 0.8897 | 7573 | 189325 | 0 | 123 | 90 | 750 | 2400 | 10 | 3200 | 1000
TET | RIGHT | Nandan Nair | PGA005 | 5.2.0 | 2025-10-01 | 2025-12-31 | 17480 | 9907 | 7573 | 0.56676 | 7573 | 189325 | 0 | 123 | 90 | 750 | 2400 | 10 | 3200 | 1000
DTech | Concerto | Sivakumar Jegannathan | PGA253 | Baseline 2.0 | 2025-05-10 | 2025-12-31 | 60711 | 58763.7 | 1947.3 | 0.96793 | 4070.95 | 101773.75 | 0 | 156 | 195 | 748.8 | 576 | 312 | 151.67 | 298.52 | 1632.96
SSsys | DMS | Srikanth G | PGA019 | 3.0.0 (RC1, RC2, Final) | 2025-07-01 | 2025-12-16 | 37416 | 39006 | -1590 | 1.0425 | 282 | 7050 | 0 |  |  |  | 128 | 40 | 64 |  |  |  | 50
V&V | TRB | Seetha LAKSHMI | PGA 037 | 6.10.7 | 2025-10-01 | 2025-12-19 | 958 | 958 | 0 | 1 | 0 | 0 | 0
V&V | STEP | Seetha LAKSHMI | PG0060 | R1.8_V2.3.0_Alpha 2 | 2025-11-10 | 2025-12-26 | 663 | 663 | 0 | 1 | 0 | 0 | 0
V&V | U400 | Kishore B V | PGA048 | ATC 15.1 | 2025-07-16 | 2025-09-23 | 4000 | 3950 | 50 | 0.9875 | 50 | 1250 | 0 | 30 |  | 20
V&V | S-HMI | Hari VEJENDLA | PGA034 | 3.2 Beta1 | 2025-06-09 | 2025-07-25 | 161 | 161 | 0 | 1 | 0 | 0 | 0
V&V | S-HMI | Hari VEJENDLA | PGA034 | 4.6.2 Beta1 | 2025-12-01 | 2025-12-19 | 255 | 255 | 0 | 1 | 0 | 0 | 0
V&V | STDS-AF | Hari VEJENDLA | PGA035 | 3.0 Beta1 | 2025-08-18 | 2025-10-03 | 519 | 519 | 0 | 1 | 0 | 0 | 0
V&V | CASCO | Hari VEJENDLA | PGA037 | 4.0.0 Beta2 | 2025-10-06 | 2025-11-14 | 1019 | 1019 | 0 | 1 | 0 | 0 | 0
V&V | Compact | Hari VEJENDLA | PGA037 | 4.1.0 Beta3 | 2025-11-17 | 2025-11-28 | 501 | 501 | 0 | 1 | 0 | 0 | 0
V&V | IVC | Hari VEJENDLA | PGA037 | 10.1.0 Beta1 | 2025-10-20 | 2025-11-21 | 1029 | 1029 | 0 | 1 | 0 | 0 | 0
V&V | WOC-NP | Hari VEJENDLA | PGA232 | 1.1.0 | 2025-04-01 | 2026-01-28 | 20148 | 19900 | 248 | 0.98769 | 248 | 6200 | 0 |  |  |  | 248
DTech | Alchemist | K Kavitha | PG0030 | Alchemist 4.60.0 | 2025-12-10 | 2025-10-12 | 4267 | 4038 | 229 | 0.94633 | 604 | 15100 | 0 | 0 | 80 | 300 | 64 | 0 | 40 | 0 | 0 | 40 | 80
DTech | Spectrail | K Kavitha | PG0030 | Spectrail 3.4.3.2 | 2025-09-30 | 9/30/2025 | 2838 | 3335 | -497 | 1.1751 | 242.5 | 6062.5 | 0 |  |  | 200 |  |  | 42.5
DTech | Spectrail | K Kavitha | PG0030 | Spectrail 3.5 | 2025-11-05 | 2025-05-11 | 1894 | 1923 | -29 | 1.0153 | 248 | 6200 | 0 |  |  | 150 |  |  | 34 |  |  |  | 64
DTech | Spectrail | K Kavitha | PG0030 | Spectrail 3.5.1 | 2025-12-19 | 12/19/2025 | 480 | 977 | -497 | 2.0354 | 264 | 6600 | 0 |  |  | 48 | 150 |  | 34 |  |  |  | 32
Mainline | CIXL-M | KALARIKKAL Shanthi | PGA026 | CIXLM_BL5.1, CIXLM_BL6.0 | 2025-04-01 | 2026-03-01 | 40000 | 38078 | 1922 | 0.95195 | 1922 | 48050 | 0 | 0 | 0 | 572 | 0 | 0 | 0 | 1350 | 0 | 0 | 0
Mainline | CIXL-M | KALARIKKAL Shanthi | PGA026 | CIXLM_BL6.0 | 2026-04-01 | 2027-03-01 |  |  | 0 | 0 | 0 | 0 | 0
AI | iSenS | Brijesh BORKAR | RDZ410 | iSenS_5.2.1 |  |  |  |  | 0 | 0 | 0 | 0 | 0
AI | iSenS | Brijesh BORKAR | RDZ410 | iSenS_5.3.0 |  |  |  |  | 0 | 0 | 0 | 0 | 0
AI | Dialogs | DAS Pradeepta | RDZ396 | 1.1.0 RC |  |  |  |  | 0 | 0 | 0 | 0 | 0
TET | MX | Gokul Krishna | PGA312 | MX infrastructure back-end Serv | 2025-10-01 | 2026-03-31 | 7069.888 | 5122.72 | 1947.168 | 0.72458 | 1947 | 48675 | 0 |  |  | 600 | 520 |  | 450 | 377
TET | RIGHT | Gokul krishna | PGA005 | 5.3.0 | 2026-01-01 | 2026-03-31 | 17016.8 | 16878.4 | 138.4 | 0.99187 | 7573 | 189325 | 0 | 123 | 90 | 750 | 2400 | 10 | 3200 | 1000
DTech | OPERA | Saket A | PG0032 | Opera BL8.5.0 | 2025-07-01 | 2027-01-15 |  |  | 0 | 0 | 0 | 0 | 0
SSsys | DMS | Srikanth G | PGA019 | BL3.0.1 | 2025-10-20 | 2026-06-15 | 51196 | 53062 | -1866 | 1.0364 | 432 | 10800 | 0 |  |  |  | 160 | 60 | 112 |  |  |  | 100
DTech | Alchemist | K Kavitha | PG0030 | V4.61.0 Alpha | 2026-01-22 | 2026-01-22 | 1530 | 1500 | 30 | 0.98039 | 56 | 1400 | 0 |  |  | 0 | 40 | 8 | 8
DTech | Spectrail | K Kavitha | PG0030 | 3.5.2 | 2026-02-10 | 2026-02-10 | 731 | 1241 | -510 | 1.6977 | 234 | 5850 | 0 |  |  | 50 | 150 |  | 34
DTech | MooN | MUTTALLI Rakesh v | PGA001 | R1.6.1 |  |  |  |  | 0 | 0 | 0 | 0 | 0
DTech | MooN | MUTTALLI Rakesh v | PGA001 | R1.6.2 |  |  |  |  | 0 | 0 | 0 | 0 | 0
DTech | MooN | MUTTALLI Rakesh v | PGA001 | R1.4.1.3 |  |  |  |  | 0 | 0 | 0 | 0 | 0
DTech | NMS | Chandrashekar BC |  | Phase5- 4.4.0 | 2026-01-02 | 2026-04-03 | 3536.3 | 3311.5 | 224.8 | 0.93643 | 225 | 5625 | 0 | 0 |  | 100 |  |  | 125
Cyber | CSP | Vijay Venugopal | PGA020 | 2.12 |  |  |  |  | 0 | 0 | 0 | 0 | 0
Cyber | CSP | Vijay Venugopal | PGA020 | 2.11 |  |  |  |  | 0 | 0 | 0 | 0 | 0
TET | CDS | Deepa Selvaraju | PGA048 | CDS_2.11 | 2025-06-06 | 2026-02-10 | 130 | 155 | -25 | 1.1923 | 0 | 0 | 0
TET | GADS | Deepa Selvaraju | PGA048 | v16.1.7 | 2026-02-01 | 2026-02-18 | 215 | 188 | 27 | 0.87442 | 27 | 675 | 0 |  | 27
TET | GADS | Deepa Selvaraju | PGA048 | v13.2.16 | 2026-02-25 | 2026-03-30 | 422 | 386 | 36 | 0.91469 | 36 | 900 | 0 |  | 36
TET | ATOM | Eswar prasad | PGA080 | 2.8.1 RC2 | 2025-12-16 | 2026-01-20 | 92 | 92 | 0 | 1 | 20 | 500 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0
TET | ATOM | Eswar prasad | PGA080 | 2.9.0 Alpha 1 | 2026-01-27 | 2026-03-02 | 261 | 261 | 0 | 1 | 70 | 1750 | 0 | 0 | 0 | 50 | 20 | 0 | 0 | 0 | 0 | 0 | 0
V&V | V&V - WOC | THANDU PARACKAL Abdul javad | PGA232 | 1.1.0 | 2025-04-01 | 2026-02-20 | 23000 | 22054 | 946 | 0.95887 | 946 | 23650 | 0 |  | 946
TET | ARAMIS | Anupama Roy | RDZ433 | 1.0.0 Beta 1 | 2025-06-01 | 2026-03-31 | 9090 | 9400 | -310 | 1.0341 | 0 | 0 | 0
DTech | Alchemist | K Kavitha | PG0030 | V4.25.1 Beta 1 | 2026-04-07 | 2026-04-07 | 434 | 425 | 9 | 0.97926 | 65 | 1625 | 0 |  |  | 9 | 40 | 8 | 8
DTech | Alchemist | K Kavitha | PG0030 | V4.62.0 | 2026-08-25 | 2026-08-25 | 3504 | Ongoing | 0 | 0 | 56 | 1400 | 0 |  |  | 20 |  | 20 | 16
V&V | U400_ATC | Kishore B | PGA048 | U400_ATC_15.2 | 2025-03-28 | 2026-08-30 |  |  | 0 | 0 | 0 | 0 | 0
V&V | U400_ATC | Kishore B | PGA048 | U400_ATC_16.1 | 2025-05-07 | 2026-08-21 |  |  | 0 | 0 | 0 | 0 | 0
TET | Syspar | Deepa Selvaraju | PGA048 | v18.6.2 | 2026-03-31 | 2026-04-22 | 308 | 232 | 76 | 0.75325 | 76 | 1900 | 0 |  | 40 |  |  |  | 36
Mainline | OCA | B M Nishitha | PGA073 | OCA 11.0 | 2025-08-18 | 2026-07-30 |  |  | 0 | 0 | 0 | 0 | 0
Urban | Fluence | MODI Sudharsan | PGA047 | BL 2242 - SGPL | 2026-01-20 | 2026-06-04 | 16830 | 16499 | 331 | 0.98033 | 325 | 8125 | 0 | 0 | 0 | 0 | 250 | 50 | 25 | 0 | 0 | 0 | 0
Urban | Fluence | MODI Sudharsan | PGA047 | BL 147 - Lille | 2026-01-20 | 2026-06-05 | 5260 | 5070 | 190 | 0.96388 | 200 | 5000 | 0 | 0 | 0 | 0 | 150 | 40 | 10 | 0 | 0 | 0 | 0
Urban | Fluence | MODI Sudharsan | PGA047 | BL 203 - Torino |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
AI | Dialogs | DAS Pradeepta | RDZ396 | Dialog_2.0.0 | Nov-1-2025 |  |  |  | 0 | 0 | 0 | 0 | 0
V&V | S-HMI | Hari VEJENDLA | PGA034 | 4.6.2 Beta2 | 2026-01-19 | 2026-03-13 | 255 | 255 | 0 | 1 | 0 | 0 | 0
V&V | S-HMI | Hari VEJENDLA | PGA034 | 4.7.1 RC1 | 2025-03-25 | 2025-04-10 | 1406 | 1406 | 0 | 1 | 0 | 0 | 0
V&V | S-HMI | Hari VEJENDLA | PGA034 | 4.8.2 Beta7 | 2026-01-05 | 2026-01-30 | 1048 | 1048 | 0 | 1 | 0 | 0 | 0
V&V | CASCO | Hari VEJENDLA | PGA037 | 4.0.0 Beta3 | 2026-02-23 | 2026-03-27 | 991 | 991 | 0 | 1 | 0 | 0 | 0
V&V | SCMT-Over-EVC3 | Hari VEJENDLA | PGA037 | 1.3.0 Alpha3 | 2025-02-10 | 2025-05-09 | 944 | 944 | 0 | 1 | 0 | 0 | 0
V&V | SCMT-Over-EVC3 | Hari VEJENDLA | PGA037 | 1.3.0 Alpha4 | 2025-11-24 | 2026-02-06 | 5275 | 5275 | 0 | 1 | 0 | 0 | 0
V&V | SCMT-Over-EVC3 | Hari VEJENDLA | PGA037 | 1.3.0 Beta1 | 2025-11-24 | 2026-04-17 | 6491 | 6491 | 0 | 1 | 0 | 0 | 0
V&V | SCMT-Over-EVC3 | Hari VEJENDLA | PGA037 | 1.3.0 Beta1 | 2026-03-02 | 2026-04-10 | 2653 | 2653 | 0 | 1 | 0 | 0 | 0
V&V | S-HMI | Hari VEJENDLA | PGA034 | 4.9.3 Beta2 | 2026-02-23 | 2026-03-20 | 679 | 679 | 0 | 1 | 0 | 0 | 0
V&V | S-HMI | Hari VEJENDLA | PGA034 | 4.7.2 Beta2 | 2026-04-13 | 2026-05-22 | 830 | 830 | 0 | 1 | 0 | 0 | 0
V&V | SCMT-Over-EVC3 | Hari VEJENDLA | PGA037 | 1.3.0 Beta2 | 2026-05-11 | 2026-06-19 | 1916 | 1916 | 0 | 1 | 0 | 0 | 0
V&V | STDS-AF | Hari VEJENDLA | PGA035 | 3.0 Beta2 | 2026-05-18 | 2026-06-19 | 528 | 528 | 0 | 1 | 0 | 0 | 0
V&V | S-HMI | Hari VEJENDLA | PGA034 | 5.6 Beta2 | 2026-04-13 | 2026-05-08 | 802 | 802 | 0 | 1 | 0 | 0 | 0
Urban | Fluence | Raviprasad Y | RDZ292 | 1.8.2 | 2025-07-23 | 2025-09-08 | 319 | 293 | 26 | 0.9185 | 26 | 650 | 0 |  | 26
Urban | Fluence | Raviprasad Y | RDZ292 | 1.6.2 | 2025-09-03 | 2025-09-11 | 165.75 | 165.75 | 0 | 1 | 0 | 0 | 0
Urban | Fluence | Raviprasad Y | RDZ292 | 2.2 | 2024-07-22 | 2025-09-19 | 3739 | 3461 | 278 | 0.92565 | 278 | 6950 | 0 |  |  |  |  | 128 | 150
DTech | Concerto | Sivakumar Jegannathan | PGA253 | Concerto Ph2.0 Final Release | 2026-01-01 | 2026-06-29 | 47662.9406 | 48605.25 | -942.3094 | 1.0198 | 5606.2565 | 140156.4118 | 0 | 299 | 260 | 1123.2 | 1320 | 499.2 | 364 | 341.1765 | 1399.68
SSsys | DMS | Srikanth G | PGA019 | BL3.1.0 | 2026-04-23 | 2026-04-23 |  |  | 0 | 0 | 0
SSsys | U400 MSS | Yogish V | PGA048 | 6.4.4.5 | 2026-01-15 | 2026-04-24 | 880 | 880 | 0 | 1 | 0 | 0 | 0
SSsys | U400 MSS | Yogish V | PGA048 | 6.5.0.5 | 2025-12-15 | 2026-04-06 | 1050 | 1170 | -120 | 1.1143 | 0 | 0 | 0
DTech | MDP | PODDUTURI Padma | RDZ385 | BL 5.0.0 | 2026-04-30 | 2026-05-25 |  |  | 0 | 0 | 0
DTech | Dialogs | DAS Pradeepta | RDZ397 | BL 2.0.0 | 2026-04-30 | 2026-06-29 |  |  | 0 | 0 | 0
AI | iSenS | Brijesh BORKAR | RDZ410 | BL 6.0.0 | 2026-06-17 | 2026-06-30 |  |  | 0 | 0 | 0
V&V | CSS | Seetha LAKSHMI | PGA002 | BL_1.6 Alpha1 | 2026-05-15 | 2026-05-15 | 408 | 408 | 0 | 1 | 0 | 0
Mainline | GE | KALARIKKAL Shanthi | PGA302 | GE 1.1.0 | 2026-06-08 | 2026-06-08 |  |  | 0 | 0 | 0
DTech | Alchemist | K Kavitha | PG0030 | V4.25.1 Beta 2 | 2026-06-24 | 2026-06-24 | 475 | 461 | 14 | 0.97053 | 15 | 375 |  |  |  | 5 |  | 10
DTech | Alchemist | K Kavitha | PG0030 | VV4.62.0 Beta 2 | 2026-09-22 | 2026-09-22 | 438 | Ongoing | 0 | 0 | 0
DTech | Spectrail | K Kavitha | PG0030 | Spectrail 3.6 | 2026-09-01 | 2026-09-01 |  | Ongoing | 0 | 0 | 0
V&V | MSTEP | Seetha LAKSHMI | PG0060 | R1.8_V2.3.0_Beta2 | 2026-06-19 | 2026-06-19 | 187 | 187 | 0 | 1 | 0 | 0
DTech | MOON | MUTTALLI Rakesh v | PGA001 | 1.5.1.2/3 | 2026-04-28 | 2026-06-30 | 1440 | 1440 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DTech | NMS | Chandrashekar BC | PGA004 | 5- 4.4.0 | 2026-04-03 | 2026-04-29 |  |  | 0 | 0 | 0
DTech | NMS | Chandrashekar BC | PGA004 | 5- 4.5.0 | 2026-04-03 | 2026-04-29 |  |  | 0 | 0 | 0
TET | RIGHT | Gokul krishna | PGA005 | 5.4.0 | 2026-04-01 | 2026-07-31 | 24565 | 19344.75 | 5220.25 | 0.78749 | 4861 | 121525 | 0 | 123 | 90 | 750 | 2788 | 10 | 100 | 1000
V&V | TRB | Seetha LAKSHMI | PGA022 | 7.7.2_B02 | 2026-03-11 | 2026-04-06 | 476 | 476 | 0 | 1 | 0 | 0
V&V | OCA | Seetha LAKSHMI | PGA022 | 10.2.1 | 2026-03-30 | 2026-06-17 | 1006 | 1006 | 0 | 1 | 0 | 0
V&V | TRK | Seetha LAKSHMI | PGA024 | 9.4.5 | 2026-04-27 | 2026-05-12 | 235 | 235 | 0 | 1 | 0 | 0
TET | GADS | Deepa Selvaraju | PGA048 | 16.1.8 | 2026-06-05 | 2026-06-05 | 380 | 392 | -12 | 1.0316 | 0 | 0 | 0
TET | Syspar | Deepa Selvaraju | PGA048 | 18.6.2.1 | 2026-04-22 | 2026-04-22 | 308 | 374 | -66 | 1.2143 | 0 | 0 | 0
TET | Syspar | Deepa Selvaraju | PGA048 | 18.6.2.2 | 2026-05-11 | 2026-05-11 | 151 | 151 | 0 | 1 | 0 | 0 | 0
TET | ATOM | Eswar prasad | PGA080 | 2.9.0 RC1 | 2026-01-21 | 2026-05-05 | 568 | 568 | 0 | 1 | 0 | 0
TET | ATOM | Eswar prasad | PGA080 | 2.9.1 RC1 | 2026-05-06 | 2026-05-21 | 278 | 278 | 0 | 1 | 0 | 0
TET | AET | Eswar prasad | PGA024 | AET TRK 2.8.0 Beta1 | 2026-06-08 | 2026-08-07 | 180 | 160 | 20 | 0.88889 | 15 | 375 | 0 | 0 |  |  | 15 | 0 | 0 | 0 | 0 | 0 | 0
TET | AET | Eswar prasad | PGA024 | RSL_DB 1.0.A_Beta1 | 2026-06-08 | 2026-08-04 | 170 | 155 | 15 | 0.91176 | 15 | 375 | 0 | 0 | 15 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
TET | AET | Eswar prasad | PGA024 | AET 2.9.0_Alpha2 | 2025-11-20 | 2026-02-27 | 250 | 260 | -10 | 1.04 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
TET | AET | Eswar prasad | PGA024 | 2.7.0_RC2 | 2025-11-19 | 2025-11-29 | 25 | 25 | 0 | 1 | 165 | 4125 | 0 | 0 |  |  | 165 | 0 | 0 | 0 | 0 | 0 | 0
TET | AET | Eswar prasad | PGA024 | 2.7.0_Beta6 | 2025-09-26 | 2025-11-18 | 210 | 200 | 10 | 0.95238 | 13 | 325 | 0 | 0 |  |  | 13 | 0 | 0 | 0 | 0 | 0 | 0
TET | AET | Eswar prasad | PGA024 | AET 2.7.0_RC1 | 2025-09-09 | 2025-09-25 | 21 | 27 | -6 | 1.2857 | 134 | 3350 | 0 | 0 |  |  | 134 | 0 | 0 | 0 | 0 | 0 | 0
TET | AET | Eswar prasad | PGA024 | 2.7.0_Beta5 | 2025-06-04 | 2025-09-08 | 240 | 225 | 15 | 0.9375 | 10 | 250 | 0 | 0 |  |  | 10 | 0 | 0 | 0 | 0 | 0 | 0
TET | AET | Eswar prasad | PGA024 | AET 2.9.0_Alpha1 | 2025-08-04 | 2025-09-04 | 270 | 290 | -20 | 1.0741 | 8 | 200 | 0 | 0 |  |  | 8 | 0 | 0 | 0 | 0 | 0 | 0
TET | AET | Eswar prasad | PGA024 | 2.7.0_Beta4 | 2025-03-26 | 2025-06-02 | 80 | 80 | 0 | 1 | 3 | 75 | 0 | 0 |  |  | 3 | 0 | 0 | 0 | 0 | 0 | 0
V&V | COMR2-GFB | Hari VEJENDLA | PGA025 | 2.0 Beta1 | 2026-04-13 | 2026-07-24 | 3340 | 3340 | 0 | 1 | 0 | 0 | 0
V&V | SCMT-Over-EVC3 | Hari VEJENDLA | PGA037 | 1.3.0 Beta2 (FT & FTVR) | 2026-07-01 | 2026-08-07 | 604 | 604 | 0 | 1 | 0 | 0 | 0
V&V | S-HMI | Hari VEJENDLA | PGA034 | 5.6 Beta4 | 2026-07-06 | 2026-09-04 | 6176 |  | 6176 | 0 | 0 | 0 | 0
V&V | S-HMI | Hari VEJENDLA | PGA034 | 4.6.2 Beta4 | 2026-07-16 | 2026-07-31 | 331 | 331 | 0 | 1 | 0 | 0 | 0
TET | AET | Eswar prasad | PGA024 | 2.7.0_Beta3 | 2024-12-20 | 2025-03-25 | 175 | 155 | 20 | 0.88571 | 20 | 500 | 0 | 0 |  |  | 20 | 0 | 0 | 0 | 0 | 0 | 0
TET | AET | Eswar prasad | PGA024 | 2.7.0_Beta2 | 2024-10-16 | 2024-12-19 | 150 | 180 | -30 | 1.2 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
TET | AET | Eswar prasad | PGA024 | 2.7.0_Beta1 | 2024-08-23 | 2024-10-15 | 170 | 145 | 25 | 0.85294 | 25 | 625 | 0 | 0 |  |  | 0 | 0 | 0 | 25 | 0 | 0 | 0
TET | AET | Eswar prasad | PGA024 | 2.7.0_Alpha | 2024-04-18 | 2024-08-22 | 300 | 340 | -40 | 1.1333 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
TET | ATOM | Eswar prasad | PGA080 | 2.6.1 | 2024-01-20 | 2024-07-10 | 211 | 211 | 0 | 1 | 0 | 0
TET | ATOM | Eswar prasad | PGA080 | 2.7.0 | 2024-07-11 | 2024-10-16 | 1804 | 1780 | 24 | 0.9867 | 24 | 600 |  |  |  | 24
TET | ATOM | Eswar prasad | PGA080 | 2.8.0 | 2024-10-17 | 2025-10-15 | 6062 | 5601 | 461 | 0.92395 | 461 | 11525 |  |  |  | 200 | 261
TET | ATOM | Eswar prasad | PGA080 | 2.8.1 | 2025-10-16 | 2026-01-20 | 797 | 749 | 48 | 0.93977 | 48 | 1200 | 0 | 0 |  |  | 0 | 0 | 0 | 48 | 0 | 0 | 0
TET | ATOM | Eswar prasad | PGA080 | 2.9.0 RC2 | 2026-05-22 | 2026-06-15 | 48 | 48 | 0 | 1 | 0 | 0
TET | JDRMDR | Eswar prasad | JDRMDR | 7.6.0 | 2024-01-01 | 2024-10-29 | 484 | 484 | 0 | 1 | 0 | 0
TET | JDRMDR | Eswar prasad | JDRMDR | 7.7.0 | 2024-10-30 | 2025-05-29 | 792 | 792 | 0 | 1 | 0 | 0
TET | JDRMDR | Eswar prasad | JDRMDR | 7.7.1 | 2025-05-30 | 2026-09-13 | 40 | 40 | 0 | 1 | 0 | 0
TET | JDRMDR | Eswar prasad | JDRMDR | 7.8.0 | 2025-09-14 | 2026-05-13 | 414 | 414 | 0 | 1 | 0 | 0
TET | JDRMDR | Eswar prasad | JDRMDR | 7.8.1 RC1 | 2025-05-14 | 2026-06-09 | 590 | 590 | 0 | 1 | 0 | 0
TET | RMR | Eswar prasad | RMR | 2.3.2 RC2 | 2024-04-01 | 2024-08-23 | 400 | 400 | 0 | 1 | 0 | 0
TET | RMR | Eswar prasad | RMR | 2.3.4 | 2024-08-25 | 2024-09-28 | 120 | 120 | 0 | 1 | 0 | 0
TET | RMR | Eswar prasad | RMR | 2.5.0 | 2024-09-29 | 2026-06-17 | 1138 | 1154 | -16 | 1.0141 | 0 | 0
TET | RMR | Eswar prasad | RMR | 2.5.1 RC1 | 2026-06-18 | 2026-08-07 | 250 | 250 | 0 | 1 | 0 | 0
TET | LAUNCHX | Eswar prasad | Launchx | 3.8.0 | 2024-04-01 | 2024-11-14 | 574 | 574 | 0 | 1 | 0 | 0
TET | LAUNCHX | Eswar prasad | Launchx | 3.8.1 | 2024-11-15 | 2026-06-17 | 264 | 264 | 0 | 1 | 0 | 0
TET | MX | Gokul Krishna | PGA312 | MX infrastructure back-end Serv | 2026-04-01 | 2026-07-31 | 11560 | 9137.25 | 2422.75 | 0.79042 | 2423 | 60575 | 0 | 0 | 250 | 560 | 640 | 0 | 570 | 403 | 0 | 0 | 0
TET | ATOM | Eswar prasad | PGA080 | 2.6.1 | 2024-01-20 | 2024-07-10 | 211 | 211 | 0 | 1 | 0 | 0
TET | ATOM | Eswar prasad | PGA080 | 2.9.1 RC2 | 2026-06-16 | 2026-07-09 | 102 | 102 | 0 | 1 | 0 | 0
TET | AET | Eswar prasad | PGA024 | RSL_DB 1.0.A_Alpha1 | 2026-03-02 | 2026-06-05 |  |  | 0 | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Forecasting
Dept | Program Name | PM Responsible | Baseline | Baseline Start | Baseline End | Estimated Hrs | Total Cost Saved from opportunities in Hrs | Total Cost Saved from opportunities in Euros | Reuse of Reference Library / Solutions in Hrs | Technical Competency Improvement in Hrs | AI Assisted / Copilot usage in Hrs | Automation of Testing - Unit / Component / System in Hrs | Automation of Reviews in Hrs | Automation of Build & Release Process - CI/CD/DevX in Hrs | Automation - Others, if any in Hrs | Usage of Simulators / Tools / Infrastruture in Hrs | Sw Development Life cycle Process Improvement / Leaner Process in Hrs | Any opportunities realised in reducing inefficiency in Hrs
Sssys | DMS | Srikanth G |  |  |  |  | 0
DTech | MooN | [5 empty] | 0
Mainline | C-IXL | Shanthi K | CIXLM_BL_6.0 | 2025-04-01 | 2027-04-01 | 500 | 100 |  |  |  | 100
DTech | CCP2 | [5 empty] | 0
DTech | OPERA | Saket Agrawal | Opera BL8.5.0 | 2025-07-01 | 2027-01-15 |  | 0
DTech | Concerto | [5 empty] | 0
TET | ARAMIS | Anupama | ARAMIS 1.1.0 | 2026-07-15 | 2027-10-30 | 3170 | 398 | 9985.82 | 0 | 0 | 314 | 0 | 0 | 84 | 0 | 0 | 0 | 0
Urban | Fluence | Sudarshan Modi | BL226 | 2026-12-05 | 2027-04-16 | 11750 | 1190 | 29857.1 |  |  | 340 | 300 | 500 | 50
Mainline | ERTMS:RBC ASW | [5 empty] | 0 | 0
Mainline | ATO | [5 empty] | 0
DTech | MDP | [5 empty] | 0
TET | AET | Manapuram Eswar Prasad | AET_TRK DB1.0.A_Alpha1 | 2026-01-07 | 2026-04-09 | 540 | 80 | 2007.2 | 4 | 0 | 40 | 4 | 0 | 0 | 32 | 0 | 0 | 0
TET | Urban - System Tools | Deepa SELVARAJU | Syspar;18.6.3.0 | 2026-08-10 | 2026-09-25 | 370 | 13 | 326.17 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
TET | RIGHT | Gokul | RIGHT SUITE 5.6.0 | 2026-01-10 | 12/31/2026 | 17340 | 435 | 10914.15 | 4 | 0 | 40 | 150 | 0 | 0 | 32 | 209 | 0 | 0
DTech | Concerto | Benjamin ROUSSEL | Platform 3.3 | 2026-07-01 | 2026-10-09 | 2106 | 122 | 3060.98 |  | 8 | 30 | 21 |  |  | 10 |  | 39 | 14
DTech | Concerto | Benjamin ROUSSEL | Platform 4.0 | 2026-10-01 | 2026-12-11 | 1685 | 150 | 3763.5 |  | 8 | 60 | 19 |  |  | 10 |  | 39 | 14
DTech | Concerto | Benjamin ROUSSEL | Platform 4.1 | 2026-12-01 | 2027-02-12 | 1685 | 115 | 2885.35 |  | 8 | 34 |  |  |  | 10 | 10 | 39 | 14
DTech | Concerto | Benjamin ROUSSEL | Platform 4.1.1 | 2027-02-01 | 2027-05-07 | 2246 | 126 | 3161.34 |  | 8 | 45 |  |  | 10 | 10 |  | 39 | 14
DTech | Concerto | Benjamin ROUSSEL | Alarm service 4.2.1 | 2026-07-01 | 2027-01-15 | 4563 | 263 | 6598.67 |  | 8 | 91 | 91 |  |  | 10 | 10 | 39 | 14
DTech | Concerto | Benjamin ROUSSEL | Alarm service 5.0.0 | 2027-01-01 | 2027-05-07 | 2948 | 259 | 6498.31 | 40 | 8 | 59 | 59 |  | 20 | 10 | 10 | 39 | 14
DTech | Concerto | Benjamin ROUSSEL | Health Monitor 1.2.0 | 2026-07-01 | 2026-09-10 | 720 | 209 | 5243.81 | 40 | 8 | 25 | 40 |  | 20 | 10 | 13 | 39 | 14